## Action Tracker
RSPO ASC Action Tracker Post February 2022 Meeting
No | Task/Activities | Topic area | PIC | Status (click on link for reference) | Action received | Action to be completed (timeline agreed) | Next step expected | Comments / Notes | [17 empty] | Weblink to final output(s) (where applicable)
1 | Secretariat to upload accepted minutes on the ASC webpage. | RSPO ASC matters | RSPO Secretariat (AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed | [16 empty] | https://www.rspo.org/resources/supporting-bodies-sc-wg-tf-/standing-committees/assurance-standing-committee/3-minutes-of-meeting
2 | Secretariat to follow up on the RT Prep Clusters format. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-11-01 |  |  | X | X | X | X | X | X | X | X | Completed
3 | Secretariat to park the budget for ASC Independent Lead and other agreed work plans in the FY21 Budget. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
4 | Secretariat to come up with a budget setting flowchart for WGs/TFs. | WG/TF | RSPO Secretariat (BT) | Closed (superceded) | 2020-03-01 | 2021-06-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | CLOSED
5 | Secretariat to remove the clause on embargo in the ToR and reword the Conflict of Interest clause. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
6 | Secretariat to update the ToR on the Contingency Plan. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
7 | BT to bring up the proposal of having everyone abide to the common RSPO CoC at the SC Alignment meeting. | RSPO ASC matters | RSPO Secretariat (BT) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
8 | ASC members to review the Labour Auditing Guidance and engage with their contacts to provide feedback. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-03-01 | 2020-11-01 |  |  | X | X | X | X | X | X | X | X | CLOSED
9 | A TF is to be formed to succeed LTF to address labour issue. | WG/TF | EK, LM, PW | Done | 2020-03-01 | 2020-09-01 |  |  | X | X | X | X | X | X | Completed
10 | Secretariat to look at engaging with WageIndicator to start discussion on labour issues. | Social & Env issue | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-09-01 |  |  | X | X | X | X | X | X | Completed
11 | The Labour Auditing Guidance should be reviewed by labour experts and piloted, before it can be endorsed by the ASC. | Social & Env issue | EK, LM, PW | Ongoing | 2020-03-01 |  | Secretariat to finalise draft based on HRWG Labour Subgroup input |  | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x
12 | PW and MC to reword the proposed solution in their proposal. | Social & Env issue | PW & MC | Done | 2020-03-01 | 2020-06-01 |  |  | X | X | X | Completed
13 | The issues on the firewalling of Complaints Desk, recruitment of CP members and who they report to,will be discussed during the meeting with CP. | ASC/CP | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
14 | Secretariat to revise the KPIs to include quantitative targets and make changes to some of the wording. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2021-04-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | Completed
15 | ASC members to bring up issues regarding IMU, shared responsibility, recruitment of experts into the CP and the building a pool of experts in the ASC-CP meeting. | ASC/CP | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
16 | Secretariat to proceed with Adam Harisson’s proposal. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
17 | Secretariat to request a more detailed proposal from the Proforest. | RSPO ASC matters | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
18 | Secretariat to send out email to the identified stakeholders informing of the change of dates and location of the first Assurance Forum. | Assurance Forum | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 | 2020-05-01 |  |  | X | X | Completed
19 | Secretariat to look into building a pool of NGOs/experts to report on non-compliances of certified units, in high risk areas. | Social & Env issue | RSPO Secretariat (WM & AMA) | Closed (superceded) | 2020-03-01 | 2020-10-01 |  |  | X | X | X | X | X | X | X | CLOSED
20 | Final comments on ASC ToR and KPIs from ASC members (by 30th June) | RSPO ASC matters | All ASC Members | Done | 2020-03-01 | 2020-03-01 |  |  | Completed
21 | ASC members to give feedbacks to the Labour Auditing Guidance & the Secretariat to follow up on the implementation plan for piloting in the next meeting. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-06-01 | 2020-11-01 | [5 empty] | X | X | X | X | X | CLOSED
22 | ASC members to suggest on the RT prep cluster format (by end of July 2020) | RSPO ASC matters | All ASC Members | Done | 2020-06-01 | 2020-08-01 | [5 empty] | X | X | Completed
23 | The Secretariat will share the independent review report to the Assurance Forum participants prior to the meeting on 26 June 2020. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-06-01 | [5 empty] | Completed
24 | Adam H will incorporate all feedbacks from the ASC Meeting and the Assurance Forum and finalise the report. | RSPO ASC matters | Adam H | Done | 2020-06-01 | 2020-06-01 |  |  | Completed
25 | The Secretariat (supported by the facilitator) will incorporate all comments on ToR and KPIs and get it back out to all ASC members (by 3rd week of July). | RSPO ASC matters | RSPO Secretariat, NJ, SPH | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
26 | The Secretariat to share the Certification Systems Document to ASC members. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | 2020-09-01 | [5 empty] | X | X | X | Completed
27 | The Secretariat will check with ASI on transparency of the CBs performance. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | 2020-11-01 | [5 empty] | X | X | X | X | X | Completed
28 | The Secretariat will update the ASC members on the HRD final report. | Social & Env issue | RSPO Secretariat | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
29 | MC & PW will take the decision of the proposal paper to the next Board meeting | Social & Env issue | MC & PW | Done | 2020-06-01 | 2020-09-01 | [8 empty] | Completed
30 | The ASC/Secretariat share the list of the Assurance Forum and re-confirm their involvement. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-12-01 | [5 empty] | X | X | X | X | X | x | Completed
31 | The ASC/Secretariat should include ASI and HCVRN in the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-06-01 | [5 empty] | Completed
32 | The ASC/Secretariat will send out MoM | RSPO ASC matters | NJ/SPH | Done | 2020-06-01 | 2020-07-01 | [5 empty] | X | Completed
33 | The ASC/Secretariat will share the proposed roles to the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | 2020-12-01 | [5 empty] | X | X | X | X | X | X | Completed
34 | The Lead Facilitator will add ‘relationship with HCSA’ included in scope of work in draft ToR, review feedback from ASC members on the draft ToR and distribute final draft of ToR to ASC members via email to sign off. | RSPO ASC matters | NJ/SPH | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
35 | The Secretariat will share ASC budget plan and activities for financial year 2020-2021. | RSPO ASC matters | RSPO Secretariat | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
36 | The Secretariat will set up a call with Co-Chairs and NJ to review the approved budget and identify any gaps on the resourcing plan for 2020-2021. | RSPO ASC matters | RSPO Secretariat | Done | 2020-09-01 | 2020-10-01 | [8 empty] | X | Completed
37 | AA will discuss all feedback received from ASC members on CBs Performance Assessment document with ASI and share the updates at the next ASC Meeting. | Certification & CBs | RSPO Secretariat | Done | 2020-09-01 | 2020-12-01 | [8 empty] | X | X | X | Completed
38 | The Secretariat will launch Fire Hub by end of Sep 2020 on limited access during a trial period before full access starts. | Social & Env issue | RSPO Secretarit | Closed (superceded) | 2020-09-01 | 2020-10-01 | [8 empty] | X | CLOSED
39 | Co-chairs of the ASC and CP will work together to identify issues for the agenda for the ASC/CP joint meeting. | ASC/CP | Co-Chairs | Done | 2020-09-01 | 2021-05-01 | [8 empty] | X | X | x | x | x | x | x | x | Completed
40 | AA will share the draft SOP for the evaluation of CB’s performance by 20th Nov 2020. | Certification & CBs | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
41 | NJ & Co-chairs will convene the forming of sub-groups within ASC to look at issues related to ASI and forming the pool of experts. | ASC sub groups | Co-chairs | Done | 2020-11-01 | 2021-05-01 | [10 empty] | x | x | x | x | x | x | Completed
42 | IMU will launch the Hotspots Hub in w/c 9th Nov 2020 | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-07-01 | [8 empty] | x | x | x | x | x | x | x | x | x | x | Completed
43 | ASC will follow up with HCVRN on the clarity of their role and contribution to ASC works. | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x | x | x | Completed
44 | The Secretariat to develop ToR to outline scope of root cause analysis and to consider a combination of internal reviews, ASI and external reviews (IUCN reviews) for this work. Overall timeline of up to 12 months is envisaged, with interim feedback/update to ASC during Q1, for discussion at the March 2021 ASC meeting | Gap analysis | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
45 | The Secretariat is to compile a list of existing gaps and other related issues. | Gap analysis | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
46 | NJ will discuss with The Secretariat and co-Chairs and will update the ASC members on the timeline for the ToR development and plan to move forward. | RSPO ASC matters | NJ, Co-chairs, RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
47 | The Secretariat will review outstanding recommendations from the ATF independent review and bring proposed actions back to ASC members before the next meeting. | WG/TF | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x | x | x | Completed
48 | The RaCP report will be made public | Social & Env issue | RSPO Secretariat | Done | 2020-11-01 | 2021-03-01 | [10 empty] | x | x |  |  | Completed
49 | The Secretariat to share RISS monitoring updates by email to get input & feedback from ASC members. | RSPO ASC matters | RSPO Secretariat | Done | 2020-11-01 | 2021-04-01 | [10 empty] | x | x | x | x | x | Completed
50 | The sub-group of ASC will aim to move forward the meeting with CP around 1st or 2nd week of December. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
51 | WM will communicate with CP on the meeting schedule. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
52 | The Assurance Forum will be conducted around 1st & 2nd week of December. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
53 | NJ will support WM on the coordination of the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
54 | The ASC/Secretariat will send out MoM | RSPO ASC matters | NJ/SPH | Done | 2020-11-01 | 2020-12-01 | [10 empty] | x | Completed
55 | NJ will support WM on the coordination of the joint ASC/CP meeting | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | 2020-12-01 | [10 empty] | x | x
56 | The Secretariat will look into feedback the proposed Assurance Forum ToR and finalise | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | 2021-06-01 | [11 empty] | x | x | x | x | x | x | Completed
57 | The Secretariat will share the ASI longer presentation with the Assurance Forum participants | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | 2020-12-01 | [11 empty] | Completed
58 | The ASC/Secretariat will send out Assurance Forum MoM | Assurance Forum | NJ/SPH | Done | 2020-12-01 | 2021-01-01 | [11 empty] | x | Completed
59 | All Assurance Forum participants to flag up key shortcomings to the Secretariat in addition to what was already highlighted in the ATF review and other reports. | Assurance Forum | AF participants | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x |  | x | Completed
60 | The Secretariat will share the update on root cause analysis with ASC members in Q1 2021 at the ASC meeting and at the next Assurance Forum in 2021. | Gap analysis | RSPO Secretariat | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x | x | x | Completed
61 | The Secretariat (TR) will follow up on HCVRN role and contribution to ASC work | RSPO ASC matters | RSPO Secretariat | Done | 2020-12-01 | 2021-04-01 | [11 empty] | x | x | x | x | Completed
62 | The Secretariat will follow up on possible date(s) for a joint meeting with CP in April. | WG/TF | RSPO Secretariat | Done | 2020-12-01 | 2021-05-01 | [11 empty] | x | x | x | x | x | Completed
63 | The Secretariat will follow up on the plan to form a sub-group of a pool of experts. | ASC sub groups | RSPO Secretariat | Ongoing | 2020-12-01 |  | Secretariat to revise proposal based on 26 Jan 2022 meeting with IMO proponents | [10 empty] | x | x | x | x | x | x | x | x
64 | NJ will liaise with TR to share the revised ASI SOP on CB performance analysis with ASC members. | Certification & CBs | NJ & RSPO Secretariat | Done | 2020-12-01 | 2021-01-01 | [12 empty] | Completed
65 | The Secretariat will be in contact with Liberty Shared to review Sime Darby allegations during February 2021. | RSPO ASC matters | RSPO Secretariat | Closed (superceded) | 2020-12-01 | 2021-03-01 | [13 empty] | x | Completed
66 | NJ & Co-chairs to follow up on meeting with HRWG. | WG/TF | NJ & Co-chairs | Done | 2020-12-01 | 2021-03-01 | [14 empty] | completed
67 | The Secretariat will share the report on FGV when finalised | RSPO ASC matters | RSPO Secretariat | Ongoing | 2021-02-01 |  | Progress update to be reported in the next meeting (May 2022) | [12 empty] | x | x | x | x | x | x
68 | At ASC Meeting April 2021: The Secretariat will share the workplan and the first result on the root cause analysis. This will identify priorities to be addressed through ASC SC and sub-groups. | ASC sub groups | RSPO Secretariat | Done | 2021-03-01 | 2021-03-01 | [14 empty] | Completed
69 | At ASC Meeting April 2021: The Secretariat, Co-chairs and NJ will identify possible working groups under the ASC. | ASC sub groups | RSPO Secretariat, Co-chairs, NJ | Done | 2021-03-01 | 2021-04-01 | [14 empty] | x | Completed
70 | The Secretariat will provide a timeline and guidance on the Decent Living Wage (DLW) for certificate holders and the CBs. | Social & Env issue | RSPO Secretariat, Co-chairs, NJ | Ongoing | 2021-03-01 |  | Progress update of DLW TF to be reported in the next meeting (May 2022) | [13 empty] | x | x | x | x | x
71 | A workshop on gap analysis for ASC members will be scheduled in early May 2021. | Gap analysis | RSPO Secretariat | Done | 2021-04-01 | 2021-05-01 | [15 empty] | x | Completed
72 | All ASC members to send further feedback and input for the draft gap analysis report. | Gap analysis | ASC members | Done | 2021-04-01 | 2021-05-01 | [15 empty] | x | Completed
73 | ASI (HdB) will share SoP of the CABs Performance Appraisal Framework for feedback and input from ASC members. | Certification & CBs | RSPO Secretariat | Done | 2021-04-01 | 2021-04-01 | [15 empty] | x | x | x | x
74 | The Secretariat (TR) will share/discuss the proposal to form a sub-group under ASC to supervise the process on MEL & Impact. | ASC sub groups | RSPO Secretariat | Closed (superceded) | 2021-04-01 |  |  | The Secretariat has decided on move ahead with this process internally, since the work straddles all units and SCs. Periodic updates to be given to the Board and SCs. | [13 empty] | x | x | x | x
75 | TR will revise the grievance systems flowchart for ASC review. | Social & Env issue | RSPO Secretariat | Closed (superceded) | 2021-04-01 | 2021-08-01 | [15 empty] | x | x | x | x
76 | The Secretariat will share the timeline on DLWTF toolkit development, as soon as available. | Social & Env issue | RSPO Secretariat | Ongoing | 2021-04-01 |  | Progress update of DLW TF to be reported in the next meeting (May 2022) | [14 empty] | x | x | x | x
77 | The Secretariat to follow up on the possibility of collaboration with Wage Indicator on DLW. | Social & Env issue | RSPO Secretariat | Ongoing | 2021-04-01 |  | Progress update of DLW TF to be reported in the next meeting (May 2022) | [14 empty] | x | x | x | x
78 | The Secretariat will launch the Fire Hub in June 2021. All ASC members to convey message to give consent for the Fire Hub reporting. | RSPO ASC matters | RSPO Secretariat | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | Completed
79 | NJ will seek ASC members’ views on including an SRWG agenda item during the next meeting. | WG/TF | NJ | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | Completed
80 | ASC members to discuss and decide in which sub-group the pool of experts should sit and what the reward mechanism is appropriate. | ASC sub groups | ASC members & The Secretariat | Ongoing | 2021-04-01 |  | Secretariat to revise proposal based on 26 Jan 2022 meeting with IMO proponents | [14 empty] | x | x | x | x
81 | The formation of ASC sub-groups will be based on the results of the root cause analysis, and prioritisation of actions. | ASC sub groups | RSPO Secretariat | Done | 2021-04-01 | 2021-07-01 | [15 empty] | x | x | x | x
82 | HRWG, and potentially ASC to set up a regular update with the Secretariat on ongoing HR investigations. | WG/TF | RSPO Secretariat | Ongoing | 2021-04-01 |  | Next steps to be determined after discussion between Integrity and Grievance Units | [14 empty] | x | x | x | x
83 | ASC will involve HRWG members in its sub-groups and regularly in meetings. | WG/TF | RSPO Secretariat | Ongoing | 2021-04-01 |  | Secretariat to follow up on invitation to participate in ASC subgroups | [14 empty] | x | x | x | x
84 | Members agreed that BHCVWG will now change its reporting line, and sit under the ASC. | WG/TF | ASC members & The Secretariat | Done | 2021-04-01 | [16 empty] | x | x | x | x
85 | CP will track information on how many certified units maintain and lose their certification after complaints are closed. | Remote audit | CP members | Done | 2021-05-01 | [17 empty] | x | x | x
86 | The Secretariat will discuss and consider mechanisms to include the CP in the CAP review process. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
87 | The Secretariat will suggest regular ASC/CP catch up meetings and to include CAP review in the discussion. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
88 | ASC and CP will choose a representative each to be involved in the process to develop the ToR for the CAP review | CAP review | RSPO Secretariat | Done | 2021-05-01 | 2021-08-01 | [16 empty] | x | x | x
89 | Final gap analysis report to provide clear distinctions between evidence-based data, cases studies and allegations. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
90 | NJ and the Secretariat will share with ASC members on nomination for sub-group to finalise root cause analysis and workplan. This will be brought back to the next ASC meeting. | Gap analysis | RSPO Secretariat & NJ | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
91 | The root cause analysis report will be shared in the next Assurance Forum. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | 2021-07-01 | [16 empty] | x | x | Completed
92 | The Secretariat to finalise the nominations for the vacant ASC member seats before the next ASC meeting. | RSPO ASC matters | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01
93 | The Secretariat to circulate draft ToR for CAP Review to the ASC members. | CAP review | RSPO Secretariat | Done | 2021-07-01 | 2021-08-01
94 | The Secretariat will incorporate comments in the gap analysis report on the alignment with CB and growers workshops and on training for growers. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-08-01
95 | The Secretariat will share the phasing of activities in the work plan with the ASC members. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01
96 | The Secretariat will publish the gap analysis report on the website. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | Report published on website on 2 Sept | [17 empty] | https://rspo.org/library/lib_files/preview/1579
97 | The Secretariat will involve MPOA in the discussion on license extension & remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | MPOA has been consulted on Scenario 5 Remote Audit draft
98 | The Secretariat will communicate the revised audit scenario 4 and present proposal for scenario 5 in the next ASC meeting in October 2021. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 | 2021-10-01 |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
99 | The Secretariat will present proposed interim decision to the BHCVWG. Feedback received from BHCVWG will then be shared with the ASC via email to get ASC's approval on interim decision. | WG/TF | RSPO Secretariat | Done | 2021-07-01 | 2021-09-01 |  | Interim decision published on website on 8 Sept 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/disclosure-and-continuity-of-certification-for-rspo-pandc-and-rspo-ish-standard
100 | The Secretariat will propose time for a sharing session with HRWG. | WG/TF | RSPO Secretariat | Closed (superceded) | 2021-07-01 | 2021-08-01
101 | MC will follow up with the co-Chair nomination from NGO representative within 2 weeks after the meeting. | RSPO ASC matters | MC | Done | 2021-10-01 | 2021-11-01 |  | Joko Sarjito (interim representative for WWF) has stepped down. New ASC Co-Chair (NGO) is Kamal Seth (new Global Palm Oil Lead for WWF Singapore)
102 | The Secretariat will confirm the designated person who responsible for follow up actions from the RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Done | 2021-10-01 |  |  | KSL from Biodiversity unit (Standards Division) will be the contact person for progress of RaCP revision
103 | The Secretariat to share plans to form Governance Subgroup to SSC for comments and advice to move forward. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01 | 2021-10-01
104 | The Secretariat will send out the template sub-group table to get nomination from ASC members until 5th Nov 2021. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01 | 2021-10-01
105 | The Secretariat to add a step in the remote audit process to accommodate independent sampling to assess effectiveness of remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-10-01 |  |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
106 | The Secretariat will pass on the proposed solutions on ISH inclusion to the Standard Division. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  |  | Secretariat will work on the relevant guidance, which is to be endorsed by the SHSC
107 | The Secretariat to send Doodle poll to determine the timing for December Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2021-10-01 | 2021-11-01
108 | The Secretariat to develop a template for members to request for revisions to their time-bound plan. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  |  | Template was published on the website on 21 Dec 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/rspo-announcement-for-time-bound-plan-revision
109 | The Secretariat to seek advice from SSC and prepare an interim solution for ASC's approval. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 | 2021-11-01
110 | The Secretariat to check with KSL & inform the ASC on progress of RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01 |  | Progress update to be reported in the next meeting (May 2022)
111 | The Secretariat to clearly define ISH to avoid confusions with scheme SH and other terms in different NIs. | ISH | RSPO Secretariat | Ongoing | 2022-02-01 |  | Secretariat to determine transition period, develop compliance guidance & update CSD
112 | The Secretariat to discuss with SDD on recommendations from the independent review of RaCP. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01 |  |  | Discussion session involving Interim Coordinator was done. Resource planning & execution to reduce RaCP backlogs are on its way. Harmonisation Workshop with the Compensation Panel scheduled for early April 2022
113 | The Secretariat to consider synergy between the HCV-HCS guidance and the CB checklist at jurisdictional level. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-02-01 |  |  | Secretariat has finalised MoU with HCSA
114 | The Secretariat to consider linking the information on CSPK produced and sold from the Dashboard with the CSPKO page on the Impacts section of the website. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01
115 | The Secretariat to plan for a systemic review of audit system document to come up with an approach to improve the elements and the gaps identified. | Audit & Remote audit | RSPO Secretariat | Ongoing | 2022-02-01
116 | The Secretariat to confirm the date for the deep-dive session on Labour in March 2022 (with HRWG, to consult with TR). | WG/TF | RSPO Secretariat | Ongoing | 2022-02-01 | 2022-03-01 | Secretariat to organise the deep-dive session | Labour Auditing Guidance draft to be presented for consultation during this session
117 | The Secretariat to cascade the concerns with the respective personnel working on the Labour Auditing Guidance. | RSPO ASC matter | RSPO Secretariat | Done | 2022-02-01
118 | The Secretariat to revert to ASC member (MC) on the specific subgroup that will discuss CBs performance and independence. | ASC sub-groups | RSPO Secretariat | Ongoing | 2022-02-01 |  |  | To be done after end of web call for participation (31 March 2022)
119 | The Secretariat to extend the deadline for call of interest for ASC subgroups on the website and provide more clarity on the ToR. | ASC sub-groups | RSPO Secretariat | Done | 2022-02-01 | 2022-03-01 | Secretariat to explore other way to increase participation | Web call for participation to end on 31 March 2022 (still low interest) | [17 empty] | https://rspo.org/news-and-events/announcements/call-for-participation-in-the-assurance-standing-committee-asc-subgroups
120

## Sheet2
Done
Closed (superceded)
Ongoing
ASC sub-groups
ASC/CP
Assurance Forum
CAP review
Certification & CBs
Gap analysis
Audit & Remote audit
RSPO ASC matter
WG/TF
ISH