## Action Tracker
RSPO ASC Action Tracker Post Nov 2024 Meeting
No | Task/Activities | Topic area | PIC | Status (click on link for reference) | Action received | Next step expected | Comments / Notes | [17 empty] | Weblink to final output(s) (where applicable)
1 | Secretariat to upload accepted minutes on the ASC webpage. | RSPO ASC matter | RSPO Secretariat (AMA) | Done | 2020-03-01 |  |  | Completed | [16 empty] | https://www.rspo.org/resources/supporting-bodies-sc-wg-tf-/standing-committees/assurance-standing-committee/3-minutes-of-meeting
2 | Secretariat to follow up on the RT Prep Clusters format. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | X | X | X | X | X | X | X | X | Completed
3 | Secretariat to park the budget for ASC Independent Lead and other agreed work plans in the FY21 Budget. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | Completed
4 | Secretariat to come up with a budget setting flowchart for WGs/TFs. | WG/TF | RSPO Secretariat (BT) | Closed (superceded) | 2020-03-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | CLOSED
5 | Secretariat to remove the clause on embargo in the ToR and reword the Conflict of Interest clause. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | Completed
6 | Secretariat to update the ToR on the Contingency Plan. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | Completed
7 | BT to bring up the proposal of having everyone abide to the common RSPO CoC at the SC Alignment meeting. | RSPO ASC matter | RSPO Secretariat (BT) | Done | 2020-03-01 |  |  | Completed
8 | ASC members to review the Labour Auditing Guidance and engage with their contacts to provide feedback. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-03-01 |  |  | X | X | X | X | X | X | X | X | CLOSED
9 | A TF is to be formed to succeed LTF to address labour issue. | WG/TF | EK, LM, PW | Done | 2020-03-01 |  |  | X | X | X | X | X | X | Completed
10 | Secretariat to look at engaging with WageIndicator to start discussion on labour issues. | Social & Env issue | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | X | X | X | X | X | X | Completed
11 | The Labour Auditing Guidance should be reviewed by labour experts and piloted, before it can be endorsed by the ASC. | Social & Env issue | EK, LM, PW | Done | 2020-03-01 |  | Field test conducted in MY and ID in Oct 2021. Draft guidance reviewed by Labour Subgroup under the HRWG in March 2022 | X | X | X | X | X | X | X | X | x | x | x | x | x | x | x | x | x
12 | PW and MC to reword the proposed solution in their proposal. | Social & Env issue | PW & MC | Done | 2020-03-01 |  |  | X | X | X | Completed
13 | The issues on the firewalling of Complaints Desk, recruitment of CP members and who they report to,will be discussed during the meeting with CP. | ASC/CP | All ASC Members | Done | 2020-03-01 |  |  | Completed
14 | Secretariat to revise the KPIs to include quantitative targets and make changes to some of the wording. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | X | X | X | X | X | X | X | X | x | x | x | x | x | Completed
15 | ASC members to bring up issues regarding IMU, shared responsibility, recruitment of experts into the CP and the building a pool of experts in the ASC-CP meeting. | ASC/CP | All ASC Members | Done | 2020-03-01 |  |  | Completed
16 | Secretariat to proceed with Adam Harisson’s proposal. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | Completed
17 | Secretariat to request a more detailed proposal from the Proforest. | RSPO ASC matter | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | Completed
18 | Secretariat to send out email to the identified stakeholders informing of the change of dates and location of the first Assurance Forum. | Assurance Forum | RSPO Secretariat (WM & AMA) | Done | 2020-03-01 |  |  | X | X | Completed
19 | Secretariat to look into building a pool of NGOs/experts to report on non-compliances of certified units, in high risk areas. | Social & Env issue | RSPO Secretariat (WM & AMA) | Closed (superceded) | 2020-03-01 |  |  | X | X | X | X | X | X | X | CLOSED
20 | Final comments on ASC ToR and KPIs from ASC members (by 30th June) | RSPO ASC matter | All ASC Members | Done | 2020-03-01 |  |  | Completed
21 | ASC members to give feedbacks to the Labour Auditing Guidance & the Secretariat to follow up on the implementation plan for piloting in the next meeting. | Social & Env issue | All ASC Members | Closed (superceded) | 2020-06-01 | [5 empty] | X | X | X | X | X | CLOSED
22 | ASC members to suggest on the RT prep cluster format (by end of July 2020) | RSPO ASC matter | All ASC Members | Done | 2020-06-01 | [5 empty] | X | X | Completed
23 | The Secretariat will share the independent review report to the Assurance Forum participants prior to the meeting on 26 June 2020. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | Completed
24 | Adam H will incorporate all feedbacks from the ASC Meeting and the Assurance Forum and finalise the report. | RSPO ASC matter | Adam H | Done | 2020-06-01 |  |  | Completed
25 | The Secretariat (supported by the facilitator) will incorporate all comments on ToR and KPIs and get it back out to all ASC members (by 3rd week of July). | RSPO ASC matter | RSPO Secretariat, NJ, SPH | Done | 2020-06-01 | [5 empty] | X | Completed
26 | The Secretariat to share the Certification Systems Document to ASC members. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | X | X | X | Completed
27 | The Secretariat will check with ASI on transparency of the CBs performance. | Certification & CBs | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | X | X | X | X | X | Completed
28 | The Secretariat will update the ASC members on the HRD final report. | Social & Env issue | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | X | Completed
29 | MC & PW will take the decision of the proposal paper to the next Board meeting | Social & Env issue | MC & PW | Done | 2020-06-01 | [8 empty] | Completed
30 | The ASC/Secretariat share the list of the Assurance Forum and re-confirm their involvement. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | X | X | X | X | X | x | Completed
31 | The ASC/Secretariat should include ASI and HCVRN in the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | Completed
32 | The ASC/Secretariat will send out MoM | RSPO ASC matter | NJ/SPH | Done | 2020-06-01 | [5 empty] | X | Completed
33 | The ASC/Secretariat will share the proposed roles to the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-06-01 | [5 empty] | X | X | X | X | X | X | Completed
34 | The Lead Facilitator will add ‘relationship with HCSA’ included in scope of work in draft ToR, review feedback from ASC members on the draft ToR and distribute final draft of ToR to ASC members via email to sign off. | RSPO ASC matter | NJ/SPH | Done | 2020-09-01 | [8 empty] | X | Completed
35 | The Secretariat will share ASC budget plan and activities for financial year 2020-2021. | RSPO ASC matter | RSPO Secretariat | Done | 2020-09-01 | [8 empty] | X | Completed
36 | The Secretariat will set up a call with Co-Chairs and NJ to review the approved budget and identify any gaps on the resourcing plan for 2020-2021. | RSPO ASC matter | RSPO Secretariat | Done | 2020-09-01 | [8 empty] | X | Completed
37 | AA will discuss all feedback received from ASC members on CBs Performance Assessment document with ASI and share the updates at the next ASC Meeting. | Certification & CBs | RSPO Secretariat | Done | 2020-09-01 | [8 empty] | X | X | X | Completed
38 | The Secretariat will launch Fire Hub by end of Sep 2020 on limited access during a trial period before full access starts. | Social & Env issue | RSPO Secretarit | Closed (superceded) | 2020-09-01 | [8 empty] | X | CLOSED
39 | Co-chairs of the ASC and CP will work together to identify issues for the agenda for the ASC/CP joint meeting. | ASC/CP | Co-Chairs | Done | 2020-09-01 | [8 empty] | X | X | x | x | x | x | x | x | Completed
40 | AA will share the draft SOP for the evaluation of CB’s performance by 20th Nov 2020. | Certification & CBs | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | x
41 | NJ & Co-chairs will convene the forming of sub-groups within ASC to look at issues related to ASI and forming the pool of experts. | ASC sub groups | Co-chairs | Done | 2020-11-01 | [10 empty] | x | x | x | x | x | x | Completed
42 | IMU will launch the Hotspots Hub in w/c 9th Nov 2020 | RSPO ASC matter | RSPO Secretariat | Done | 2020-11-01 | [8 empty] | x | x | x | x | x | x | x | x | x | x | Completed
43 | ASC will follow up with HCVRN on the clarity of their role and contribution to ASC works. | RSPO ASC matter | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | x | x | x | Completed
44 | The Secretariat to develop ToR to outline scope of root cause analysis and to consider a combination of internal reviews, ASI and external reviews (IUCN reviews) for this work. Overall timeline of up to 12 months is envisaged, with interim feedback/update to ASC during Q1, for discussion at the March 2021 ASC meeting | Gap analysis | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | Completed
45 | The Secretariat is to compile a list of existing gaps and other related issues. | Gap analysis | RSPO Secretariat | Closed (superceded) | 2020-11-01 | [10 empty] | x | x
46 | NJ will discuss with The Secretariat and co-Chairs and will update the ASC members on the timeline for the ToR development and plan to move forward. | RSPO ASC matter | NJ, Co-chairs, RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | Completed
47 | The Secretariat will review outstanding recommendations from the ATF independent review and bring proposed actions back to ASC members before the next meeting. | WG/TF | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | x | x | x | Completed
48 | The RaCP report will be made public | Social & Env issue | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | x |  |  | Completed
49 | The Secretariat to share RISS monitoring updates by email to get input & feedback from ASC members. | RSPO ASC matter | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | x | x | x | x | Completed
50 | The sub-group of ASC will aim to move forward the meeting with CP around 1st or 2nd week of December. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | [10 empty] | x | x
51 | WM will communicate with CP on the meeting schedule. | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | [10 empty] | x | x
52 | The Assurance Forum will be conducted around 1st & 2nd week of December. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | Completed
53 | NJ will support WM on the coordination of the Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2020-11-01 | [10 empty] | x | Completed
54 | The ASC/Secretariat will send out MoM | RSPO ASC matter | NJ/SPH | Done | 2020-11-01 | [10 empty] | x | Completed
55 | NJ will support WM on the coordination of the joint ASC/CP meeting | WG/TF | RSPO Secretariat | Closed (superceded) | 2020-11-01 | [10 empty] | x | x
56 | The Secretariat will look into feedback the proposed Assurance Forum ToR and finalise | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | [11 empty] | x | x | x | x | x | x | Completed
57 | The Secretariat will share the ASI longer presentation with the Assurance Forum participants | Assurance Forum | RSPO Secretariat | Done | 2020-12-01 | [11 empty] | Completed
58 | The ASC/Secretariat will send out Assurance Forum MoM | Assurance Forum | NJ/SPH | Done | 2020-12-01 | [11 empty] | x | Completed
59 | All Assurance Forum participants to flag up key shortcomings to the Secretariat in addition to what was already highlighted in the ATF review and other reports. | Assurance Forum | AF participants | Done | 2020-12-01 | [11 empty] | x | x |  | x | Completed
60 | The Secretariat will share the update on root cause analysis with ASC members in Q1 2021 at the ASC meeting and at the next Assurance Forum in 2021. | Gap analysis | RSPO Secretariat | Done | 2020-12-01 | [11 empty] | x | x | x | x | Completed
61 | The Secretariat (TR) will follow up on HCVRN role and contribution to ASC work | RSPO ASC matter | RSPO Secretariat | Done | 2020-12-01 | [11 empty] | x | x | x | x | Completed
62 | The Secretariat will follow up on possible date(s) for a joint meeting with CP in April. | WG/TF | RSPO Secretariat | Done | 2020-12-01 | [11 empty] | x | x | x | x | x | Completed
63 | The Secretariat will follow up on the plan to form a sub-group of a pool of experts. | ASC sub groups | RSPO Secretariat | Closed (superceded) | 2020-12-01 | See item 147 | [10 empty] | x | x | x | x | x | x | x | x | https://www.rspo.org/news-and-events/announcements/expression-of-interest-project-management-team-for-pool-of-experts
64 | NJ will liaise with TR to share the revised ASI SOP on CB performance analysis with ASC members. | Certification & CBs | NJ & RSPO Secretariat | Done | 2020-12-01 | [12 empty] | Completed
65 | The Secretariat will be in contact with Liberty Shared to review Sime Darby allegations during February 2021. | RSPO ASC matter | RSPO Secretariat | Closed (superceded) | 2020-12-01 | [13 empty] | x | Completed
66 | NJ & Co-chairs to follow up on meeting with HRWG. | WG/TF | NJ & Co-chairs | Done | 2020-12-01 | [14 empty] | completed
67 | The Secretariat will share the report on FGV when finalised | RSPO ASC matter | RSPO Secretariat | Done | 2021-02-01 |  | FGV Post Complaints Monitoring had been completely handed over to the Grievance unit in February 2022. | [11 empty] | x | x | x | x | x | x
68 | At ASC Meeting April 2021: The Secretariat will share the workplan and the first result on the root cause analysis. This will identify priorities to be addressed through ASC SC and sub-groups. | ASC sub groups | RSPO Secretariat | Done | 2021-03-01 | [14 empty] | Completed
69 | At ASC Meeting April 2021: The Secretariat, Co-chairs and NJ will identify possible working groups under the ASC. | ASC sub groups | RSPO Secretariat, Co-chairs, NJ | Done | 2021-03-01 | [14 empty] | x | Completed
70 | The Secretariat will provide a timeline and guidance on the Decent Living Wage (DLW) for certificate holders and the CBs. | Social & Env issue | RSPO Secretariat, Co-chairs, NJ | Done | 2021-03-01 |  | Proposed revision to indicator 6.2.6 incorporated into P&C 2023 draft (new indicator num. 6.3.2) | [12 empty] | x | x | x | x | x
71 | A workshop on gap analysis for ASC members will be scheduled in early May 2021. | Gap analysis | RSPO Secretariat | Done | 2021-04-01 | [15 empty] | x | Completed
72 | All ASC members to send further feedback and input for the draft gap analysis report. | Gap analysis | ASC members | Done | 2021-04-01 | [15 empty] | x | Completed
73 | ASI (HdB) will share SoP of the CABs Performance Appraisal Framework for feedback and input from ASC members. | Certification & CBs | RSPO Secretariat | Done | 2021-04-01 | [15 empty] | x | x | x | x
74 | The Secretariat (TR) will share/discuss the proposal to form a sub-group under ASC to supervise the process on MEL & Impact. | ASC sub groups | RSPO Secretariat | Closed (superceded) | 2021-04-01 |  | The Secretariat has decided on move ahead with this process internally, since the work straddles all units and SCs. Periodic updates to be given to the Board and SCs. | [13 empty] | x | x | x | x
75 | TR will revise the grievance systems flowchart for ASC review. | Social & Env issue | RSPO Secretariat | Closed (superceded) | 2021-04-01 | [15 empty] | x | x | x | x
76 | The Secretariat will share the timeline on DLWTF toolkit development, as soon as available. | Social & Env issue | RSPO Secretariat | Ongoing | 2021-04-01 | Living Wage TF approved the ToR for the development of the Prevailing Wage Calculation Procedure (PWCP), endorsed by the SSC on 2 April 2024. Living Wage Task Force met on 24 October 2024, where a revised timeline for developing the PWCP to meet the November 2025 deadline was shared. | [14 empty] | x | x | x | x
77 | The Secretariat to follow up on the possibility of collaboration with Wage Indicator on DLW. | Social & Env issue | RSPO Secretariat | Done | 2021-04-01 | Contacts & proposal from WageIndicator has been shared with the HRSS who will lead the Worker Voice project. (see item 82). | [14 empty] | x | x | x | x
78 | The Secretariat will launch the Fire Hub in June 2021. All ASC members to convey message to give consent for the Fire Hub reporting. | RSPO ASC matter | RSPO Secretariat | Done | 2021-04-01 | [15 empty] | x | x | x | Completed
79 | NJ will seek ASC members’ views on including an SRWG agenda item during the next meeting. | WG/TF | NJ | Done | 2021-04-01 | [15 empty] | x | x | x | Completed
80 | ASC members to discuss and decide in which sub-group the pool of experts should sit and what the reward mechanism is appropriate. | ASC sub groups | ASC members & The Secretariat | Closed (superceded) | 2021-04-01 | Refer item 147 | [14 empty] | x | x | x | x
81 | The formation of ASC sub-groups will be based on the results of the root cause analysis, and prioritisation of actions. | ASC sub groups | RSPO Secretariat | Done | 2021-04-01 | [15 empty] | x | x | x | x
82 | HRWG to give regular update to the ASC on ongoing HRWG activities that are relevant to Assurance. | WG/TF | RSPO Secretariat | Ongoing | 2021-04-01 | The HRSS unit has identified a few Worker Voice tools and is restarting the discussion with the identified organisations. Updates will be given to the ASC when available. | [14 empty] | x | x | x | x
83 | ASC will involve HRWG members in its sub-groups and regularly in meetings. | WG/TF | RSPO Secretariat | Closed (superceded) | 2021-04-01 | HRWG members had been invited to join the ASC subgroups in 2022 but no interest received. | [14 empty] | x | x | x | x
84 | Members agreed that BHCVWG will now change its reporting line, and sit under the ASC. | WG/TF | ASC members & The Secretariat | Done | 2021-04-01 | [15 empty] | x | x | x | x
85 | CP will track information on how many certified units maintain and lose their certification after complaints are closed. | Remote audit | CP members | Done | 2021-05-01 | [16 empty] | x | x | x
86 | The Secretariat will discuss and consider mechanisms to include the CP in the CAP review process. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
87 | The Secretariat will suggest regular ASC/CP catch up meetings and to include CAP review in the discussion. | CAP review | RSPO Secretariat | Closed (superceded) | 2021-05-01 |  | Grievance Unit has been moved to CEO's office on 15 Nov 2021 | [14 empty] | x | x | x
88 | ASC and CP will choose a representative each to be involved in the process to develop the ToR for the CAP review | CAP review | RSPO Secretariat | Done | 2021-05-01 | [16 empty] | x | x | x
89 | Final gap analysis report to provide clear distinctions between evidence-based data, cases studies and allegations. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | [16 empty] | x | x | Completed
90 | NJ and the Secretariat will share with ASC members on nomination for sub-group to finalise root cause analysis and workplan. This will be brought back to the next ASC meeting. | Gap analysis | RSPO Secretariat & NJ | Done | 2021-05-01 | [16 empty] | x | x | Completed
91 | The root cause analysis report will be shared in the next Assurance Forum. | Gap analysis | RSPO Secretariat | Done | 2021-05-01 | [16 empty] | x | x | Completed
92 | The Secretariat to finalise the nominations for the vacant ASC member seats before the next ASC meeting. | RSPO ASC matter | RSPO Secretariat | Done | 2021-07-01
93 | The Secretariat to circulate draft ToR for CAP Review to the ASC members. | CAP review | RSPO Secretariat | Done | 2021-07-01
94 | The Secretariat will incorporate comments in the gap analysis report on the alignment with CB and growers workshops and on training for growers. | Gap analysis | RSPO Secretariat | Done | 2021-07-01
95 | The Secretariat will share the phasing of activities in the work plan with the ASC members. | Gap analysis | RSPO Secretariat | Done | 2021-07-01
96 | The Secretariat will publish the gap analysis report on the website. | Gap analysis | RSPO Secretariat | Done | 2021-07-01 |  | Report published on website on 2 Sept | [17 empty] | https://rspo.org/library/lib_files/preview/1579
97 | The Secretariat will involve MPOA in the discussion on license extension & remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 |  | MPOA has been consulted on Scenario 5 Remote Audit draft
98 | The Secretariat will communicate the revised audit scenario 4 and present proposal for scenario 5 in the next ASC meeting in October 2021. | Audit & Remote audit | RSPO Secretariat | Done | 2021-07-01 |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
99 | The Secretariat will present proposed interim decision to the BHCVWG. Feedback received from BHCVWG will then be shared with the ASC via email to get ASC's approval on interim decision. | WG/TF | RSPO Secretariat | Done | 2021-07-01 |  | Interim decision published on website on 8 Sept 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/disclosure-and-continuity-of-certification-for-rspo-pandc-and-rspo-ish-standard
100 | The Secretariat will propose time for a sharing session with HRWG. | WG/TF | RSPO Secretariat | Closed (superceded) | 2021-07-01
101 | MC will follow up with the Co-Chair nomination from NGO representative within 2 weeks after the meeting. | RSPO ASC matter | MC | Done | 2021-10-01 |  | Joko Sarjito (interim representative for WWF) has stepped down. New ASC Co-Chair (NGO) is Kamal Seth (new Global Palm Oil Lead for WWF Singapore)
102 | The Secretariat will confirm the designated person who responsible for follow up actions from the RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Done | 2021-10-01 |  | KSL from Biodiversity unit (Standards Division) will be the contact person for progress of RaCP revision
103 | The Secretariat to share plans to form Governance Subgroup to SSC for comments and advice to move forward. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01
104 | The Secretariat will send out the template sub-group table to get nomination from ASC members until 5th Nov 2021. | ASC sub-groups | RSPO Secretariat | Done | 2021-10-01
105 | The Secretariat to add a step in the remote audit process to accommodate independent sampling to assess effectiveness of remote audits. | Audit & Remote audit | RSPO Secretariat | Done | 2021-10-01 |  | Contingency Audit Procedure ver 2 published on website on 30 Nov 2021 | [17 empty] | https://www.rspo.org/library/lib_files/preview/1638
106 | The Secretariat will pass on the proposed solutions on ISH inclusion to the Standard Division. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  | Secretariat will work on the relevant guidance, which is to be endorsed by the SHSC
107 | The Secretariat to send Doodle poll to determine the timing for December Assurance Forum. | Assurance Forum | RSPO Secretariat | Done | 2021-10-01
108 | The Secretariat to develop a template for members to request for revisions to their time-bound plan. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01 |  | Template was published on the website on 21 Dec 2021 | [17 empty] | https://www.rspo.org/news-and-events/announcements/rspo-announcement-for-time-bound-plan-revision
109 | The Secretariat to seek advice from SSC and prepare an interim solution for ASC's approval. | Certification & CBs | RSPO Secretariat | Done | 2021-10-01
110 | The Secretariat to check with KSL & inform the ASC on progress of RaCP implementation review. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2022-02-01 | As BHCVWG requested to analyse RaCP V2 components, the Secretariat has identified elements that require refinement before the public consultation process. A workshop will take place in February 2025 to communicate the progress on the analysis with the BHCVWG on RaCP V2 and to receive their direction on the next steps.
111 | The Secretariat to clearly define ISH to avoid confusions with scheme SH and other terms in different NIs. | ISH | RSPO Secretariat | Done | 2022-02-01 |  | This was resolved with BoG's endorsement of the RSPO Management System Requirement for Group Certification of FFB on 18 May 2022 (modified on 18 Aug 2022) | [17 empty] | https://www.rspo.org/library/lib_files/preview/1863
112 | The Secretariat to discuss with SDD on recommendations from the independent review of RaCP. | RSPO ASC matter | RSPO Secretariat | Done | 2022-02-01 |  | Biodiversity Unit is working closely with an external consultant on RaCP v2. More details in line item 110.
113 | The Secretariat to consider synergy between the HCV-HCS guidance and the CB checklist at jurisdictional level. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-02-01 | The JA-BHCV sub-working group met on 19 Sep to review the draft with RSPO Secretariat (JA unit) and HCVN. The responses from the subgroup were positive, with minor suggestions for improvement. Pending presentation to the full Jurisdictional Working Group (JWG) for their information and final feedback. If no issue is found with the JWG, then we can proceed with endorsement by the SSC, with the earliest possibility in March 2025.
114 | The Secretariat to consider linking the information on CSPK produced and sold from the Dashboard with the CSPKO page on the Impacts section of the website. | Audit & Remote audit | RSPO Secretariat | Done | 2022-02-01 |  | Information on supply and sales of CSPKO has been published in the Impacts section of the website in July 2023. | [17 empty] | https://rspo.org/our-impact/outcomes-and-impacts/
115 | The Secretariat to plan for a systemic review of audit system document to come up with an approach to improve the elements and the gaps identified. | Audit & Remote audit | RSPO Secretariat | Done | 2022-02-01 |  | Updates on certification systems revision to be presented in this meeting.
116 | The Secretariat to confirm the date for the deep-dive session on Labour in March 2022 (with HRWG, to consult with TR). | WG/TF | RSPO Secretariat | Done | 2022-02-01 |  | Draft guidance reviewed by Labour Subgroup under the HRWG in March 2022
117 | The Secretariat to cascade the concerns with the respective personnel working on the Labour Auditing Guidance. | RSPO ASC matter | RSPO Secretariat | Done | 2022-02-01
118 | The Secretariat to revert to ASC member (MC) on the specific subgroup that will discuss CBs performance and independence. | ASC sub-groups | RSPO Secretariat | Done | 2022-02-01 |  | Standards Quality Subgroup will discuss this matter and MC has agreed to participate (26 Apr 2022)
119 | The Secretariat to extend the deadline for call of interest for ASC subgroups on the website and provide more clarity on the ToR. | ASC sub-groups | RSPO Secretariat | Done | 2022-02-01 |  | Web call ended on 31 March 2022. Standards Quality Subgroup was formed first with 6 members. | [17 empty] | https://rspo.org/news-and-events/announcements/call-for-participation-in-the-assurance-standing-committee-asc-subgroups
120 | The Secretariat to incorporate the ASC’s comments into the Contingency RSPO Audit Procedure - for Supply Chain Standard (Version 2). | Audit & Remote audit | RSPO Secretariat | Done | 2022-05-01 |  | Document published on 30 June 2022 | [17 empty] | https://rspo.org/news-and-events/announcements/contingency-rspo-audit-procedure-for-supply-chain-standard--updated-version
121 | The Secretariat to channel the ASC’s suggestions on ensuring stakeholders’ confidentiality & safety in remote audits to the P&C Review Task Force. | Audit & Remote audit | RSPO Secretariat | Done | 2022-05-01 |  | WM shared suggestions on 3 Aug 2022 to the P&C Review Task Force
122 | The Secretariat to upload the Assurance Progress report on the ASC webpage | Gap analysis | RSPO Secretariat | Done | 2022-05-01 |  | Report published on the ASC webpage | [17 empty] | https://rspo.org/library/lib_files/preview/1833
123 | The Secretariat to channel feedback from the RSPO ISH Training for Auditors to the Smallholder Unit. | ISH | RSPO Secretariat | Done | 2022-05-01
124 | The Secretariat to channel the ASC’s suggestions on shared learning among growers to the Training Unit under the Technical Division. | Certification & CBs | RSPO Secretariat | Done | 2022-05-01
125 | The GIS team to develop a proposal to improve the sanction mechanism for land clearings on uncertified units. | Certification & CBs | RSPO Secretariat | Ongoing | 2022-05-01 | To refine once RaCP v2 is endorsed, as the mechanism relies on the same land clearing form process. The RaCP v2 draft is proposed to be postponed to allocate adequate time for gap assessment and impact evaluation.
126 | The GIS team to work with Certification Unit on resolution GA18-2c for deforestation monitoring to enhance the robustness of the Mass Balance model. | Certification & CBs | RSPO Secretariat | Closed (superceded) | 2022-05-01 |  | The Proforest’s MB Robustness Study report was accepted by the SSC on 28 Feb 2023. The Secretariat will need to ensure collaboration across different efforts of different departments (i.e. Digital Framework) in resolving the findings of the report. MDSC to take the lead on the supply chain 1:1 conversion matter; including communication on the RSPO MB Model.
127 | The Secretariat to urgently carry out the actions agreed by the BHCVWG in 2020 to revise the system for identifying and remedying social liabilities. (RaCP Implementation Review) | Certification & CBs | RSPO Secretariat | Done | 2022-05-01 |  | Social remediation elements have been included in draft RaCP v2 (related to item 110).
128 | The Secretariat to send the Secretariat's performance survey to the ASC by 20 May 2022. | RSPO ASC matter | RSPO Secretariat | Done | 2022-05-01 |  | Survey sent via SurveyMonkey on 20 May 2022
129 | The Secretariat to consolidate the agenda for the June 2022 ASC-CP meeting. | ASC/CP | RSPO Secretariat | Done | 2022-05-01 |  | Meeting held on 16 June 2022
130 | List of action items from ASC-CP Joint Meeting on 16 June 2022: - RSPO will share the number of respondents for each complaint in the analysis. - RSPO team will follow up with details on labour violations and note under which ILO indicators. - The Secretariat to compare ILO requirements with relevant national interpretations in the analysis for complaints related to labour issues. - The Secretariat to clarify which alleged social violations are major or minor and what indicators are being used to identify them. - The Secretariat to set up time to present analysis on RSPO audit’s framework (management system vs performance based). - The Secretariat to share suggestions relating to grievance mechanisms in operating units from this meeting with the P&C Review Task Force. (Done) - The Secretariat to strengthen the auditing for new planting procedures to identify social issues as early as possible. - The Secretariat to share the suggestion with the P&C Review Task Force that supplementary guidance and tools should be launched together with standards revision. (Done) - The Secretariat to develop guidance to increase capacity of auditors for social audit. - The Secretariat will share the list of action points and the next steps, soonest possible. - The Secretariat to set up a quarterly meeting and share relevant documents a week before the meeting. | ASC/CP | RSPO Secretariat | Closed (superceded) | 2022-06-01 |  | Has been discussed at the BoG meeting in June 2022. The following has been agreed: The CP Co-Chairs are to liaise with the ASC Co-Chairs and move this topic of “social auditing concerns"" to a more structured discussion under the ambit of the ASC, which can then come up with a solution and recommendation for board consideration. A meeting between ASC & CP Co-Chairs will be organised in Oct 2022 to discuss way forward. Proposed topics for the ASC-CP Co-Chairs meeting in Oct 2022 were discussed in the Sept meeting.
131 | The Secretariat to incorporate the SSC and ASC’s comments to finalise the Labour Auditing Guidance and publish it on the website as a voluntary guidance document for trial usage of 18 months. | Audit & Remote audit | RSPO Secretariat | Done | 2022-09-01 | [19 empty] | https://rspo.org/rspo-labour-auditing-guidance-based-on-the-rspo-principles-criteriahandbook-for-auditors/
132 | The Secretariat to develop a ToR for the independent review of the Labour Auditing Guidance prior to the end of the 18 months trial period. | Audit & Remote audit | RSPO Secretariat | Done | 2022-09-01 |  | Further action under item 155.
133 | The Certification Unit to revise section 5.7.3 of the Certification Systems Document 2020 to include the statement on minimum 4 estates to be audited, and publish it in the RSPO Interpretation Forum (RIF). | Certification & CBs | RSPO Secretariat | Done | 2022-09-01 |  | Revision to 5.7.3 of the CSD 2020 was announced in the RIF on 26 Oct 2022
134 | The Secretariat to discuss with HCVN on a standardised way to monitor HCV areas in RSPO members’ concessions. | ASC sub-groups | RSPO Secretariat | Closed (superceded) | 2022-09-01 |  | Through the new prisma platform, the Secretariat will compile shapefiles of members’ concessions consisting of HCV, HCS, peat and other areas. This will allow for better monitoring of the HCV areas.
135 | The Secretariat to immediately start working on the second study on de-linking CBs with certificate holders. | Audit & Remote audit | RSPO Secretariat | Done | 2022-09-01
136 | The Secretariat to develop a code of conduct for auditors for the next revision of the certification system. | Audit & Remote audit | RSPO Secretariat | Done | 2022-09-01 |  | The Code has now been included as Annex 11 in the new cert syst document.
137 | The Secretariat to organise a physical ASC meeting on 1 December 2022 (during RT 2022). | RSPO ASC matter | RSPO Secretariat | Done | 2022-09-01 |  | Meeting held on 1 Dec 2022, 930am - 12pm, in hybrid mode (physical at Shangri-La hotel KL, online via Zoom)
138 | The Secretariat to work with the ASC’s Social NGO constituent on draft proposal for improvement on social auditing. | Audit & Remote audit | RSPO Secretariat | Closed (superceded) | 2022-09-01 |  | See item 141
139 | The Secretariat to present a draft ToR for the second study on de-linking CBs with certificate holders in Q1 2023 ASC meeting. | Certification & CBs | RSPO Secretariat | Done | 2022-12-22 |  | Draft ToR was revised based on ASC comments in Q1 2023 meeting, then discussed with Standards Quality Subgroup before being tabled in ASC Q3 2023 meeting.
140 | The Secretariat to present a draft code of conduct for auditors in Q1 2023 ASC meeting. | Certification & CBs | RSPO Secretariat | Done | 2022-12-23 |  | Draft code of conduct was discussed in Q1 2023 meeting.
141 | ASC’s social NGO representative to share ideas for improvement on social auditing with the Secretariat. | Certification & CBs | RSPO Secretariat | Done | 2022-12-24 |  | The ASC’s sNGO rep was on the interviewee list for the independent review of the Labour Auditing Guidance implementation. Marcus Colchester was interviewed by Proforest on 14 June 2024.
142 | The Secretariat to present proposals for worker voice tools from Ulula and Wage Indicator in Q1 2023 ASC meeting. | Audit & Remote audit | RSPO Secretariat | Done | 2022-12-25
143 | The Secretariat to share points of discussion with the ASC on draft P&C 2023 with the P&C Review Task Force. | WG/TF | RSPO Secretariat | Done | 2022-12-26 |  | ASC's input for the P&C was shared with the task force on 4 Jan 2023
144 | The Secretariat to share the P&C 2018 generic checklist for auditors with the ASC. | Certification & CBs | RSPO Secretariat | Done | 2022-12-27 |  | Sent together with draft MoM on 16 Dec 2022
145 | The Secretariat to convey the ASC’s suggestion on strengthening social aspects in the Metrics Template to the Impacts Team. | Audit & Remote audit | RSPO Secretariat | Done | 2022-12-28 |  | Done and being incorporated into prisma.
146 | ASI to present their recommendations regarding the witness effect in the Q1 2023 ASC meeting. | Certification & CBs | RSPO Secretariat | Done | 2022-12-29
147 | The Secretariat to connect with PW to recommend a project management team for PoE. | Audit & Remote audit | RSPO Secretariat | Closed (superceded) | 2022-12-30 |  | See item 166
148 | The Secretariat to send proposed dates for all ASC activities in 2023. | RSPO ASC matter | RSPO Secretariat | Done | 2022-12-31 |  | Calendar invites for all ASC meetings and Assurance Forums in 2023 have been sent
149 | The Secretariat to consider ASC’s comments on the proposed RaCP tracker before publishing it on the website. | Gap analysis | RSPO Secretariat | Done | 2023-03-23 |  | ASC’s comments have been considered and the RaCP tracker has been published on the website. | [17 empty] | https://rspo.org/as-an-organisation/tools/remediation-and-compensation/racp-trackers/
150 | The Secretariat to revise the draft code of conduct for auditors and send to the ASC for online approval one month after this meeting. | Certification & CBs | RSPO Secretariat | Done | 2023-03-23 |  | Revised draft was sent for ASC's online approval on 28 Apr 2023
151 | The Secretariat to pass the approved code of conduct for RSPO auditors to ASI for implementation and monitoring. | Certification & CBs | RSPO Secretariat | Closed (superceded) | 2023-03-23 |  | See item 161
152 | The Secretariat to review the Ulula and WageIndicator proposals and restrategise the way forward. | Gap analysis | RSPO Secretariat | Closed (superceded) | 2023-03-23 |  | This action item has been passed to HRSS to avoid duplication of work.
153 | The Secretariat to revise the ToR for initial study on de-linking business relations between CBs and auditees and discuss it with the Standards Quality Subgroup before bringing it back to the Q3 ASC meeting (29 August 2023). | Gap analysis | RSPO Secretariat | Done | 2023-03-23
154 | The Secretariat to explore another way to report progress of the Assurance Gap Analysis work plan instead of producing Assurance Progress reports. | Gap analysis | RSPO Secretariat | Done | 2023-03-23 |  | Remaining action items from the Assurance Gap Analysis work plan has been reviewed and turned into Assurance Action Plans 2024-2026 and presented to the ASC in Q3 2024. Progress update will be given in Q1 meeting every year.
155 | The Secretariat to involve the HRWG in reviewing the ToR for the Independent Review of the Labour Auditing Guidance and selecting the consultant after receiving proposals. | Gap analysis | RSPO Secretariat | Done | 2023-06-23 |  | HRWG reviewed and approved the ToR and was consulted in the Secretariat's internal evaluation of the 3 proposals received. | [17 empty] | https://rspo.org/call-for-proposal-independent-review-of-the-implementation-of-rspo-labour-auditing-guidance/
156 | The Secretariat to submit the revised NPP 2021 Verification Checklist for Auditors for online approval by the ASC within three weeks. | Gap analysis | RSPO Secretariat | Done | 2023-06-23 |  | Email for online approval sent on 3 July 2023
157 | The Biodiversity Unit to connect with the FICG to ensure financial institution representation in the BHCVWG and publish the approved ToR on the RSPO website. | Gap analysis | RSPO Secretariat | Done | 2023-06-23 |  | HSBC approached for potential representation. Revised ToR published on 26 June 2023.
158 | The Secretariat to share a summary of the discussion on ASI Insights on Agropalma’s Suspension for the June 2023 BoG meeting. | RSPO ASC matter | RSPO Secretariat | Done | 2023-06-23 |  | Notes for BoG June meeting sent on 16 June 2023
159 | The Secretariat to prepare a brief response to the IUCN NL letter for the June 2023 BoG meeting. | RSPO ASC matter | RSPO Secretariat | Done | 2023-06-23 |  | Notes for BoG June meeting sent on 16 June 2023
160 | The Secretariat to revise the Draft ToR for Initial Study on De-Linking Business Relations Between RSPO-Accredited Certification Bodies and Auditees and publish it on the website in Sept 2023. | RSPO ASC matter | RSPO Secretariat | Done | 2023-08-23 |  | Call for proposal published on 12 Sept 2023 | [17 empty] | https://rspo.org/call-for-proposal-initial-study-on-de-linking-business-relations-between-rspo-accredited-certification-bodies-and-auditees/
161 | The Secretariat to revise the Code of Conduct for RSPO Auditors based on ASI’s and the ASC’s suggestions in this meeting and to check with the SSC on the possibility for immediate implementation of the Code. | RSPO ASC matter | RSPO Secretariat | Done | 2023-08-23 |  | SSC agreed for the Secretariat to conduct internal analysis. Feedback gathered from CBs, ASI and internal legal review was presented to the ASC. CoC has been included as Annex 11 in the new certification systems.
162 | The Secretariat to share reasons behind delays and deviations to TBP in the next ASC meeting. | Certification & CBs | RSPO Secretariat | Ongoing | 2023-08-23 | Put on hold until prisma goes live, as it will allow for more accurate and comprehensive data analysis.
163 | The Secretariat to share (i) actual scale of outstanding liabilities compared to what has been processed in the last 5 years, (ii) if RaCP is being processed at the speed that was mandated within the guidance and what has improved since the Secretariat increased its capacity and (iii) the quality and consistency of the reviewers’ and the Compensation Panels’ decisions, in the next meeting. | Social & Env issue | RSPO Secretariat | Done | 2023-08-23 |  | Presented to the ASC in Q4 2023 meeting.
164 | The Secretariat to give an update on Agropalma’s surveillance audit following the lifting of suspension in the next meeting. | Certification & CBs | RSPO Secretariat | Done | 2023-08-23 |  | Update given to ASC in Feb 2024 meeting. Suspension of Agropalma’s certificate was effective as of 29 Nov 2023 and will last for 6 months. This was based on clause 5.9.4.a of the RSPO Certification Systems Document 2020.
165 | The Secretariat to arrange for a meeting with the Co-Chairs and IUCN NL during RT 2023. | RSPO ASC matter | RSPO Secretariat | Done | 2023-08-23 |  | Meeting held on 22 Nov 2023 during RT2023.
166 | PW to circulate the previous ToR (April 2022) to gather the ASC’s suggestions on how to form the Pool of Experts to cover a broader scope than the ToR that was published in Sept 2022. | Audit & Remote audit | RSPO Secretariat | Closed (superceded) | 2023-08-23 |  | See item 168
167 | The Secretariat to standardise the format of ASC decision papers moving forward. | RSPO ASC matter | RSPO Secretariat | Done | 2023-11-30 |  | Decision papers are now formalised, as demonstrated by the selection of a vendor for the "Independent Review of the Implementation of RSPO Labour Auditing Guidance" in Q1 2024 meeting.
168 | The Secretariat to discuss the challenges of the PoE formation with the Co-Chairs. | RSPO ASC matter | RSPO Secretariat | Done | 2023-11-30 |  | Discussed with CP Co-chairs in Feb 2024. Raised again at Q1 2024 ASC meeting, with the suggestion of commissioning a consultant to help develop this database of experts. This is now part of the new RSPO strategic pillars plan
169 | The Secretariat to map the outcomes from the Assurance Breakout at RT2023 and discussion within the ASC during Q4 2023 meeting into an action plan consisting of ongoing and new measures to be taken. The action plan will be presented in the Q2 2024 meeting. | RSPO ASC matter | RSPO Secretariat | Done | 2023-11-30 |  | Presented to the ASC in Q3 2024. Progress update will be given in Q1 meeting every year.
170 | The Secretariat to get online approval for the Extension of Interim Measures for Disclosure and Continuity of Certification for P&C and RISS within a week. | Certification & CBs | RSPO Secretariat | Done | 2023-11-30 |  | Online approval process began on 6 Dec and the decision was finalised on 26 Dec. The announcement was published on 29 Dec 2023 | [17 empty] | https://rspo.org/extension-of-interim-measures-for-disclosure-and-continuity-of-certification-for-rspo-standard/
171 | The Secretariat to conduct an internal evaluation (using an evaluation matrix) and make recommendation for the 3 de-linking proposals before getting online endorsement from the ASC within a week. | Certification & CBs | RSPO Secretariat | Done | 2023-11-30 |  | Online approval process began on 6 Dec and the decision was finalised on 26 Dec. NewForesight was chosen as the consultant to conduct this study
172 | The Secretariat to present the draft framework for review of accreditation body’s performance in the next meeting. | Gap analysis | RSPO Secretariat | Done | 2023-11-30 |  | Initial framework presented in Q1 2024 meeting. Detailed mechanism presented in Q3 2024 meeting. See item 186
173 | The Secretariat to send calendar invites for upcoming meetings in 2024. | RSPO ASC matter | RSPO Secretariat | Done | 2023-11-30 |  | Dates have been adjusted to avoid clashing with SSC and BoG meetings
174 | The Secretariat to publish an announcement to clarify the continued voluntary status of the Labour Auditing Guidance until the BoG mandates otherwise. | RSPO ASC matter | RSPO Secretariat | Done | 2024-02-23 |  | Announcement posted on 20 March 2024. | [17 empty] | https://rspo.org/continuation-of-voluntary-status-for-the-rspo-labour-auditing-guidance/
175 | The Secretariat to proceed with the appointment of Proforest for the independent review of the Labour Auditing Guidance, with the addition of interviews with local civil society organisations and labour unions. | RSPO ASC matter | RSPO Secretariat | Done | 2024-02-24 |  | Proforest was appointed and work started in April 2024
176 | The Secretariat to send a Doodle poll to set the first ASC-CP joint meeting in 2024. The agenda will include updates on compliance to EUDR. | ASC/CP | RSPO Secretariat | Done | 2024-02-25
177 | The Secretariat to ask NewForesight to elaborate further on the characteristics and conditions for the alternative delinking model, i.e., the central fund model, to be revisited in the future. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2024-05-29 | NewForesight has shared additional interview responses for the study - only those in response to the questions about the central fund model, and interviewees were anonymised except by category. To be shared with the ASC in 2025.
178 | The Secretariat to initiate internal discussion for collaboration with universities aimed at expanding the pool of auditors. | RSPO ASC matter | RSPO Secretariat | Done | 2024-05-29 |  | This initiative has been added into RSPO-ASI joint long-term workplan, which will be shared with the ASC in Q1 2025.
179 | The Secretariat to get online approval for the Code of Conduct revision. | RSPO ASC matter | RSPO Secretariat | Done | 2024-05-29 |  | The online approval process started on 6 June and was finalised on 13 June 2024. The Secretariat has included the Code of Conduct as Annex 11 in the revised certification systems.
180 | The Secretariat to share the announcement for vacant seats in the ASC for members to circulate it within their networks. | RSPO ASC matter | RSPO Secretariat | Done | 2024-05-29 | [19 empty] | https://rspo.org/call-for-e-ngo-and-retailer-participation-in-the-asc/
181 | The Secretariat to send a Doodle poll for the physical ASC meeting around RT2024. | RSPO ASC matter | RSPO Secretariat | Done | 2024-05-29
182 | The Secretariat will share all the slides presented and requested in this meeting with the ASC and CP Co-Chairs. | RSPO ASC matter | RSPO Secretariat | Done | 2024-05-31 |  | Slides shared on 9 June
183 | The Secretariat to resolve matters regarding Rainforest Alliance’s participation as E-NGO representative in the ASC. | RSPO ASC matter | RSPO Secretariat | Done | 2024-08-28
184 | The Secretariat to discuss with Standards Division whether the timeline for guidance needs analysis can be brought forward so that any guidance document(s) can be ready before the end of the transition period for the new P&C. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2024-08-28 | To be raised with the Standards Division.
185 | The Secretariat to confirm with the Biodiversity Unit whether input from BHCVWG was taken into account in the P&C review. | ASC sub groups | RSPO Secretariat | Done | 2024-08-28 |  | The BHCVWG submitted formal comments for the P&C review for which the review team has addressed each concern.
186 | The Secretariat to revise the draft AB Performance Appraisal based on the ASC’s feedback including: 360 review for any required improvements for RSPO and a mid-term review process in addition to the full appraisal (every 5 years). | RSPO ASC matter | RSPO Secretariat | Ongoing | 2024-08-28 | The revised mechanism for the AB Performance Appraisal will be presented in Q1 2025 meeting.
187 | The Secretariat to raise the AB capacity issue to the CEO for discussion at the ISEAL Alliance. | RSPO ASC matter | RSPO Secretariat | Closed (superceded) | 2024-08-28 | This matter has been escalated to the CEO. Given that ASI is the only AB within the ISEAL Alliance, the Secretariat will adopt two strategic approaches to strengthen ASI’s capacity: (i) finalising and implementing the AB Performance Appraisal, and (ii) enhancing collaboration with ASI by co-developing a long-term work plan. This plan will encompass initiatives such as annual calibration programs involving CB auditors and ASI assessors, establishing a risk-based auditing mechanism, and collaborating on complementary training for identified regions. Once ready, this plan will be shared with the ASC in 2025. | From Q4 2024 meeting: ASC emphasised the need for the CEO to address AB capacity and availability at the ISEAL Alliance, as RSPO cannot resolve this alone. This item is now superceded with item 191.
188 | The Secretariat to share the ASC's comments regarding the MoU with HCVN with the Standards Division. | RSPO ASC matter | RSPO Secretariat | Done | 2024-08-28 |  | The ASC’s feedback about the MoU with HCVN has been shared with the Standards Division. The Standards Division highlighted that the MoU is still a generic document to demonstrate planned collaboration and further details will be later fleshed out, guided partly by the ASC’s feedback.
189 | The Secretariat to send a calendar invite for the Q4 Physical ASC Meeting in Bangkok. | RSPO ASC matter | RSPO Secretariat | Done | 2024-08-28 |  | A calendar invite & Zoom link have been shared for a hybrid meeting on Sunday, 10 Nov 2024, 5pm to 8pm (GMT+7) at Novotel Bangkok)
190 | The Secretariat to proceed with the appointment of Lee Swee Yin from SD Guthrie as an alternate member for the Malaysian grower seat in the ASC. | RSPO ASC matter | RSPO Secretariat | Done | 2024-08-28 |  | Appointment finalised on 9 Sept 2024
191 | The Secretariat to raise the AB capacity issue to the CEO for discussion at the ISEAL Alliance - to be tabled at the Q1 2025 meeting. | RSPO ASC matter | RSPO Secretariat | Ongoing | 2024-11-10 | Updates from raising to the ISEAL Alliance - RSPO discussion to be given at Q12025.
192 | The Secretariat to publish the full LAG review study on the RSPO website. | Social & Env issue | RSPO Secretariat | Done | 2024-11-10 |  | Action completed. The study was published on 26 Nov 2024. | [17 empty] | https://rspo.org/report-on-independent-review-of-rspo-labour-auditing-guidance-lag/
193 | The Secretariat to identify workstreams based on findings of the Independent Review of LAG and present it in the next meeting. | Social & Env issue | RSPO Secretariat | Ongoing | 2024-11-10 | Work streams to be identified and presented to the ASC in Q1 2025 meeting.
194 | The Secretariat to incorporate concrete recommendations from the Independent Review of LAG in the new CSD. | Social & Env issue | RSPO Secretariat | Ongoing | 2024-11-10 | A workshop will be held in early January 2025.
195 | The results of the Independent Review of LAG Implementation to be presented in the next SSC meeting. | Social & Env issue | RSPO Secretariat | Done | 2024-11-10 |  | Action completed. Proforest presented the results at the SSC meeting on 5 Dec 2024
196 | The Secretariat to share the updated timeline for CSD after GA21. | Certification & CBs | RSPO Secretariat | Done | 2024-11-10 |  | Action completed. Standards rollout timeline is attached to email sent to the ASC on 9 Dec 2024.
197 | The Secretariat to share a more detailed proposal regarding focused audits and uncertified management units for online consultation with the ASC in January 2025 (ensuring alignment with the CSD revision deadline). | Certification & CBs | RSPO Secretariat | Ongoing | 2024-11-10 | Updates to be given to ASC in Q1 2025 meeting.

## Dropdown Field Options
Done
Closed (superceded)
Ongoing
RSPO ASC matter
WG/TF
Social & Env issue
ASC/CP
Assurance Forum
Certification & CBs
ASC sub groups
Gap analysis
Remote audit
CAP review
Audit & Remote audit
ASC sub-groups
ISH

## Chart Playground
| Done - 157 | Superseded / Closed - 27 | Ongoing - 13 | Total
Total action items - 197 | 157 | 27 | 13 | 197